## Sheet1
Task Name | Owner | Date | Status | Remarks
Planning | Systems Analyst |  |  | Planning and Analysis of the project
Requirement Elicitation Plan | Business Analyst | 2020-02-10 | Completed
Development Plan | Product Development Manager | 2020-03-06 | Completed
Data Migration Plan | DBA Team | 2020-03-17 | Completed
Testing Planning | Test Lead | 2020-03-20 | Completed
Training Planning | Project Manager | 2020-03-23 | Completed
Architecture planning | Product Development Manager | 2020-03-30 | Completed
Development Activities | Product Development Manager |  |  | Fornt end and back end application development
Database | Development Team | 2020-04-03 | Completed
Application | Development Team | 2020-04-06 | Completed
UI | Development Team | 2020-04-09 | Completed
Integrations | Development Team | 2020-04-13 | Completed
Reports | Development Team | 2020-04-14 | Completed
Testing Activities | Test Lead |  | Completed | End-to-end testing of the system. All test cases passed.
Unit Testing | Development Team | 2020-04-04 | Completed
Performance Testing | Test Team | 2020-04-14 | Completed
Regression Testing | Test Team | 2020-04-14 | Completed
Integration Testing | Test Team | 2020-04-14 | Completed
Stress Testing | Test Team | 2020-04-16 | Completed
Documentation Prep | Business Analyst |  |  | Requirement gathering and analysis. Feasibility study and business rules for community guidelines acquired.
Specific Requirement Document | Business Analyst | 2020-03-06 | Completed
Developer Documentation | Development Team | 2020-04-14 | Completed
User documentation | Business Analyst | 2020-03-13 | Completed
Community Guidelines Document | Legal Associate | 2020-03-18 | Completed
FAQ document | Business Analyst | 2020-05-18 | In Progress
Training | L&D Manager |  |  | Preparing employees of the corporation to handle data processes
User training development | L&D Consultant | 2020-04-17 | Completed
User training review | L&D Consultant | 2020-04-17 | Completed
User training rollout | L&D Consultant | 2020-04-17 | Completed
Rollout | Support & Maintenance Team Lead |  |  | Deployment of the application into the existing system.
Infrastructure Prep | Product Development Manager | 2020-04-17 | Completed
License structure | Legal Associate | 2020-04-17 | Completed
Deployment | DBA Team | 2020-04-24 | Completed
Development Resource Reallocation | Systems Analyst | 2020-04-17 | Completed
Data Migration steps | DBA Team | 2020-04-22 | Completed
User set up | Support & Maintenance Team | 2020-04-23 | Completed
Report & Metrics Development | Business Analyst | 2020-05-18 | In Progress
User training | L&D Consultant | 2020-04-20 | Completed
Database Rollback steps | DBA Team | 2020-04-24 | Completed
Application Rollback steps | Support & Maintenance Team | 2020-04-24 | Completed
Day 0 Deployment | Support & Maintenance Team | 2020-04-24 | Completed
Support set up | Support & Maintenance Team | 2020-04-21 | Completed
Week 1 support plan | Support & Maintenance Team | 2020-05-06 | Completed
Week 1 daily review meeting | Support & Maintenance Team | 2020-05-06 | Completed
Week 2 support plan | Support & Maintenance Team | 2020-05-13 | In Progress
Week 2 biweekly review meeting | Support & Maintenance Team | 2020-05-13 | In Progress
Post rollout | Support & Maintenance Team | 2020-05-20 | In Progress
Resource Reallocation | Systems Analyst | 2020-05-21 | In Progress